## Slide 1: Agile Methodologies Redux
Rinku Gupta Argonne National Laboratory
Software Productivity and Sustainability track, ATPESC 2021
Contributors: Rinku K. Gupta (ANL), Michael A. Heroux (SNL), James M. Willenbring (SNL)

## Slide 2: License, Citation and Acknowledgements
License and Citation
This work is licensed under a Creative Commons Attribution 4.0 International License (CC BY 4.0).
The requested citation the overall tutorial is: David E. Bernholdt, Anshu Dubey, Rinku K. Gupta, and David M. Rogers, Software Productivity and Sustainability track, in Argonne Training Program on Extreme-Scale Computing (ATPESC), online, 2021. DOI: 10.6084/m9.figshare.15130590
Individual modules may be cited as Speaker, Module Title, in Better Scientific Software tutorial…
Acknowledgements
This work was supported by the U.S. Department of Energy Office of Science, Office of Advanced Scientific Computing Research (ASCR), and by the Exascale Computing Project (17-SC-20-SC), a collaborative effort of the U.S. Department of Energy Office of Science and the National Nuclear Security Administration.
This work was performed in part at the Argonne National Laboratory, which is managed by UChicago Argonne, LLC for the U.S. Department of Energy under Contract No. DE-AC02-06CH11357.
This work was performed in part at the Oak Ridge National Laboratory, which is managed by UT-Battelle, LLC for the U.S. Department of Energy under Contract No. DE-AC05-00OR22725.
This work was performed in part at the Lawrence Livermore National Laboratory, which is managed by Lawrence Livermore National Security, LLC for the U.S. Department of Energy under Contract No. DE-AC52-07NA27344.
This work was performed in part at the Los Alamos National Laboratory, which is managed by Triad National Security, LLC for the U.S. Department of Energy under Contract No.89233218CNA000001
This work was performed in part at Sandia National Laboratories. Sandia National Laboratories is a multi-mission laboratory managed and operated by National Technology and Engineering Solutions of Sandia, LLC., a wholly owned subsidiary of Honeywell International, Inc., for the U.S. Department of Energy’s National Nuclear Security Administration under contract DE-NA0003525.

## Slide 3: Outline
Refining our Epic
PSIP: Productivity and Sustainability Improvement Planning

## Slide 4: More on Epic, Story, Task
Definition of Done
Refining Issues
Agile Estimation

## Slide 5: Epic, Story, Task Review
Break down and refine when and as needed
  Close to when the work will be done
  Only for work that will take place
  Can be valuable for estimating
  There is no “correct” level of granularity
Epics are very high level objectives
Stories should represent an increment of value to the customer
  “Definition of Done” – understandable to user
Tasks are the steps necessary to complete a story
  May not individually provide value to the customer

## Slide 6: Definition of Done
Simplified definition: When all acceptance criteria are met
Acceptance criteria
  “Conditions that a software product must satisfy to be accepted by a user, customer or stakeholder.” – Microsoft Press
  “Pre-established standards or requirements a product or project must meet.” – Google
  Can include functional, non-functional, and performance requirements.

## Slide 7: Definition of Done
Important to establish for a story before estimating or beginning a task
Defined by the team, acceptable to customer
  Customer language
Should not specify an implementation unnecessarily

## Slide 8: Refining Our Epic
Epic: Refactor code for enhanced modularity
  Description: The heat equation code needs refactoring to improve modularity. Specifically, there are utilities that could be generalized and used with for other applications. Also, the integration function is currently hard-coded. In the future, we want to use alternative integration functions, so we should generalize the interface for this function.
  Story 1: Separate out utilities
    Definition of Done
    Task list
  Story 2: Separate out integration function
    Definition of Done
    Task list

## Slide 9: Refining Our Epic
  Story 1: Separate out utilities
    Definition of Done
      Unit tests pass
      Code review completed
      Integration/system tests pass
      Utility performance is at least 95% of pre-separation performance
      Utility usability demonstrated outside of heat equation application
  Story 2: Separate out integration function
    Task 1: Add testing for integration function to protect functionality during refactor
      Needed testing should be specified
    Task 2: Generalize interface to allow alternative implementations
    Task 3: Expose current integration function through the new interface & run tests

## Slide 10: Agile Estimation
Estimating is hard
  Requires practice
  With practice, it is still hard
Stories are estimated using “story points”
  Relative estimate
  Many estimating techniques
  Should NOT map to hours, days, etc
  Definition of done needed, tasking not required
Tasks are estimated in hours
  Absolute estimate
Useful for planning schedules
Key concept:
It is easier to accurately estimate many small tasks than to estimate a large epic.
Epic: Huge refactor effort
Tasks:
Add tests
Generalize interface
Expose existing interface

## Slide 11: How To Get Better
“Use iteration and incrementation only for projects you want to succeed.”
Adaptation of Martin Fowler quote

## Slide 12: Strategy for Incremental Productivity Improvements
Identify, analyze, prototype, test, revise, deploy. Repeat.
Realistic: There is a cost.
  Startup: Overhead
  Payoff: Best if soon, clear
Working model:
  Reserve acceptable time/effort for improvement.
  Improve how you do your work on the way to getting it done.
  Repeat.
Cost
Progress
Start
Finish
Old Process
New Process

## Slide 13: Productivity and Sustainability Improvement Planning (PSIP) Examples: EXAALT & MPICH
MPICH PSIP: Onboarding new team members
EXAALT PSIP: Continuous integration (CI) testing
BSSw blog article: Adopting Continuous Integration for Long Timescale Materials Simulation, Rick Zamora (Sept 2018)
PSIP workflow helps a team create user stories, identify areas for improvement, select a specific area and topic for a single improvement cycle, and then develop those improvements with specific metrics for success.
https://bssw.io/psip